PHASE 4

Project Planning Phase

AnswerBot – AI-Powered FAQ and Customer Support Automation

| Field | Details |
| --- | --- |
| Project Title | AnswerBot – AI-Powered FAQ and Customer Support Automation |
| Team ID | SWTID-2026-3079 |

# 1. Project Objectives

- Build a secure REST API for FAQ management with AI-assisted content generation.

- Provide keyword search and category-based organisation.

- Test all endpoints and deliver complete documentation and a demo.

# 2. Work Breakdown and Timeline

| Sprint | Duration | Tasks | Deliverable |
| --- | --- | --- | --- |
| Sprint 1 | Week 1 | Ideation, requirement gathering, tool setup | Problem statement, requirement list |
| Sprint 2 | Week 2 | Architecture, ER design, API design, project setup | Design document, folder structure |
| Sprint 3 | Week 3 | Database connection, User and FAQ models, authentication | Working register and login |
| Sprint 4 | Week 4 | FAQ CRUD, search, Gemini integration, error handling | Complete API |
| Sprint 5 | Week 5 | Testing, bug fixing, Postman collection | Test report |
| Sprint 6 | Week 6 | Documentation, demo preparation, final review | Final submission |

Adjust the durations to match your own schedule.

# 3. Milestones

| Milestone | Description | Target |
| --- | --- | --- |
| M1 | Requirements and design approved | End of Week 2 |
| M2 | Authentication and database ready | End of Week 3 |
| M3 | All modules completed | End of Week 4 |
| M4 | Testing completed | End of Week 5 |
| M5 | Documentation and demo ready | End of Week 6 |

# 4. Roles and Responsibilities

| Member | Responsibility |
| --- | --- |
| [Name 1] | Backend development: routes, controllers, middleware |
| [Name 2] | Database design and Mongoose models |
| [Name 3] | AI integration with Google Gemini |
| [Name 4] | Testing and documentation |

# 5. Tools and Resources

- VS Code

- Node.js and npm

- MongoDB (local or Atlas)

- Postman / ThunderClient

- Git and GitHub

- Google AI Studio (Gemini API key)

# 6. Risk Management

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Gemini API failure or rate limit | AI features unavailable | Return a clear error message; allow manual FAQ creation. |
| Database connection issues | API downtime | Validate the connection string; use retry and logging. |
| Token or secret leakage | Security breach | Keep secrets in .env and out of version control. |
| Schedule delay | Late delivery | Prioritise core features; keep a buffer week. |
| Invalid user input | Bad data | Use schema validation and validation middleware. |